## Cover
Cybersecurity Risk and ITGC Assessment
Engagement | Example Bank Lab cybersecurity risk and ITGC assessment
Snapshot | SNAP-20260926T024908-88653414
Frozen at | 2026-09-26T02:49:08.830858Z
Review mode | self_reviewed
Boundary | Synthetic local lab; self-reviewed; no assurance opinion
PDF status | Pending; HTML documents are print-ready

## Scope
Type | Statement
Scope | Local portal application and synthetic PostgreSQL data
Scope | Application identity, access, change, logging, backup and recovery controls
Scope | Canonical assessment records and sanitized portfolio exports
Exclusion | Real banking infrastructure, customers, money and payment rails
Exclusion | Independent audit opinion, certification and complete regulatory compliance assessment

## Assets
Asset ID | Snapshot ID
ASSET-PORTAL | SNAP-20260926T024908-88653414

## Risk Register
Risk ID | Control IDs
RISK-CHG-01 | CHG-01
RISK-CHG-02 | CHG-02
RISK-CHG-03 | CHG-03
RISK-CHG-04 | CHG-04
RISK-DR-01 | DR-01
RISK-DR-02 | DR-02
RISK-GOV-01 | GOV-01
RISK-GOV-02 | GOV-02
RISK-GOV-03 | GOV-03
RISK-IAM-01 | IAM-01
RISK-IAM-02 | IAM-02
RISK-IAM-03 | IAM-03
RISK-IAM-04 | IAM-04
RISK-IAM-05 | IAM-05
RISK-IR-01 | IR-01
RISK-IR-02 | IR-02
RISK-OPS-01 | OPS-01
RISK-OPS-02 | OPS-02
RISK-OPS-03 | OPS-03
RISK-OPS-04 | OPS-04

## Control Register
Control ID | Domain | Owner role | Frequency | Workpaper ID | Design status | Operating status
CHG-01 | change | simulated_change_approver | per_event | WP-CHG-01-LIMITATION | not_assessed | not_tested
CHG-02 | change | simulated_change_approver | per_event | WP-CHG-02-LIMITATION | not_assessed | not_tested
CHG-03 | change | simulated_system_administrator | per_release | WP-CHG-03-LIMITATION | not_assessed | not_tested
CHG-04 | change | simulated_change_approver | per_event | WP-CHG-04-LIMITATION | not_assessed | not_tested
DR-01 | recovery | simulated_system_administrator | annual | WP-DR-01-LIMITATION | not_assessed | not_tested
DR-02 | recovery | simulated_system_administrator | per_exercise | WP-DR-02-LIMITATION | not_assessed | not_tested
GOV-01 | governance | project_owner_assessor | assessment_start | WP-GOV-01-LIMITATION | not_assessed | not_tested
GOV-02 | governance | project_owner_assessor | quarterly | WP-GOV-02-LIMITATION | not_assessed | not_tested
GOV-03 | governance | simulated_supplier_owner | annual | WP-GOV-03-LIMITATION | not_assessed | not_tested
IAM-01 | access | simulated_system_administrator | per_event | WP-IAM-01-LIMITATION | not_assessed | not_tested
IAM-02 | access | simulated_system_administrator | per_event | WP-IAM-02-S01 | adequate | exceptions_identified
IAM-03 | access | simulated_system_administrator | continuous | WP-IAM-03-LIMITATION | not_assessed | not_tested
IAM-04 | access | simulated_system_administrator | per_session | WP-IAM-04-LIMITATION | partially_adequate | effective_in_tested_scope
IAM-05 | access | simulated_change_approver | quarterly | WP-IAM-05-LIMITATION | not_assessed | not_tested
IR-01 | incident | simulated_system_administrator | continuous | WP-IR-01-LIMITATION | not_assessed | not_tested
IR-02 | incident | simulated_system_administrator | per_incident | WP-IR-02-LIMITATION | not_assessed | not_tested
OPS-01 | operations | simulated_system_administrator | per_batch | WP-OPS-01-LIMITATION | partially_adequate | effective_in_tested_scope
OPS-02 | operations | simulated_system_administrator | per_exercise | WP-OPS-02-LIMITATION | not_assessed | not_tested
OPS-03 | operations | simulated_system_administrator | continuous | WP-OPS-03-LIMITATION | partially_adequate | effective_in_tested_scope
OPS-04 | operations | project_owner_assessor | per_release | WP-OPS-04-LIMITATION | not_assessed | not_tested

## Workpapers
Workpaper ID | Control ID | Test type | Evidence IDs | Design status | Operating status | Review mode
WP-CHG-01-LIMITATION | CHG-01 | combined | EVID-POL-04 | not_assessed | not_tested | self_reviewed
WP-CHG-02-LIMITATION | CHG-02 | inspection | EVID-POL-04 | not_assessed | not_tested | self_reviewed
WP-CHG-03-LIMITATION | CHG-03 | reperformance | EVID-POL-04 | not_assessed | not_tested | self_reviewed
WP-CHG-04-LIMITATION | CHG-04 | inspection | EVID-POL-05 | not_assessed | not_tested | self_reviewed
WP-DR-01-LIMITATION | DR-01 | inspection | EVID-POL-07 | not_assessed | not_tested | self_reviewed
WP-DR-02-LIMITATION | DR-02 | reperformance | EVID-POL-07 | not_assessed | not_tested | self_reviewed
WP-GOV-01-LIMITATION | GOV-01 | inspection | EVID-POL-01 | not_assessed | not_tested | self_reviewed
WP-GOV-02-LIMITATION | GOV-02 | inspection | EVID-POL-10 | not_assessed | not_tested | self_reviewed
WP-GOV-03-LIMITATION | GOV-03 | inspection |  | not_assessed | not_tested | self_reviewed
WP-IAM-01-LIMITATION | IAM-01 | inspection | EVID-POL-01 | not_assessed | not_tested | self_reviewed
WP-IAM-02-S01 | IAM-02 | combined | EVID-POL-02;EVID-S01-BASELINE;EVID-S01-POPULATION | adequate | exceptions_identified | self_reviewed
WP-IAM-03-LIMITATION | IAM-03 | combined | EVID-POL-01 | not_assessed | not_tested | self_reviewed
WP-IAM-04-LIMITATION | IAM-04 | combined | EVID-POL-03;EVID-S03-BASELINE;EVID-S03-RETEST | partially_adequate | effective_in_tested_scope | self_reviewed
WP-IAM-05-LIMITATION | IAM-05 | inspection | EVID-POL-03 | not_assessed | not_tested | self_reviewed
WP-IR-01-LIMITATION | IR-01 | combined | EVID-POL-09 | not_assessed | not_tested | self_reviewed
WP-IR-02-LIMITATION | IR-02 | walkthrough |  | not_assessed | not_tested | self_reviewed
WP-OPS-01-LIMITATION | OPS-01 | combined | EVID-POL-06;EVID-S05-BASELINE;EVID-S05-RETEST | partially_adequate | effective_in_tested_scope | self_reviewed
WP-OPS-02-LIMITATION | OPS-02 | reperformance | EVID-POL-06;EVID-POL-07 | not_assessed | not_tested | self_reviewed
WP-OPS-03-LIMITATION | OPS-03 | combined | EVID-POL-08;EVID-S06-BASELINE;EVID-S06-RETEST | partially_adequate | effective_in_tested_scope | self_reviewed
WP-OPS-04-LIMITATION | OPS-04 | inspection | EVID-POL-10 | not_assessed | not_tested | self_reviewed

## Evidence Index
Evidence ID | Provenance | Classification | Media type | Collected at
EVID-POL-01 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-02 | authored_policy | sanitized | text/markdown | 2026-09-25T13:45:00Z
EVID-POL-03 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-04 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-05 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-06 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-07 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-08 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-09 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-POL-10 | authored_policy | sanitized | text/markdown | 2026-09-26T02:00:55Z
EVID-S01-BASELINE | observed_lab | sanitized | application/json | 2026-09-25T14:00:00Z
EVID-S01-POPULATION | synthetic_record | sanitized | application/json | 2026-09-25T13:55:00Z
EVID-S01-RETEST | observed_lab | sanitized | application/json | 2026-09-25T15:10:00Z
EVID-S03-BASELINE | observed_lab | sanitized | application/json | 2026-09-26T02:07:20Z
EVID-S03-RETEST | observed_lab | sanitized | application/json | 2026-09-26T02:08:20Z
EVID-S05-BASELINE | observed_lab | sanitized | application/json | 2026-09-26T02:07:20Z
EVID-S05-RETEST | observed_lab | sanitized | application/json | 2026-09-26T02:08:20Z
EVID-S06-BASELINE | observed_lab | sanitized | application/json | 2026-09-26T02:07:20Z
EVID-S06-RETEST | observed_lab | sanitized | application/json | 2026-09-26T02:08:20Z

## Findings
Finding ID | Control IDs | Rating | Status | Evidence IDs | Owner role | Target date
FIND-S01-001 | IAM-02 | 20 | closed_verified | EVID-POL-02;EVID-S01-BASELINE | simulated_system_administrator | 2026-10-09
FIND-S03-001 | IAM-04 | 16 | closed_verified | EVID-S03-BASELINE | simulated_system_administrator | 2026-10-10
FIND-S05-001 | OPS-01 | 20 | closed_verified | EVID-S05-BASELINE | simulated_system_administrator | 2026-10-10
FIND-S06-001 | OPS-03 | 16 | closed_verified | EVID-S06-BASELINE | simulated_system_administrator | 2026-10-10

## Remediation
finding_id | control_ids | risk_rating | finding_status | owner_role | effort | target_date | action_id | action_status | retest_id | retest_result | closure_decision
FIND-S01-001 | IAM-02 | 20 | closed_verified | simulated_system_administrator | small | 2026-10-09 | ACT-S01-001 | implemented | RETEST-S01-001 | passed | accept_closure
FIND-S03-001 | IAM-04 | 16 | closed_verified | simulated_system_administrator | small | 2026-10-10 | ACT-S03-001 | implemented | RETEST-S03-001 | passed | accept_closure
FIND-S05-001 | OPS-01 | 20 | closed_verified | simulated_system_administrator | small | 2026-10-10 | ACT-S05-001 | implemented | RETEST-S05-001 | passed | accept_closure
FIND-S06-001 | OPS-03 | 16 | closed_verified | simulated_system_administrator | small | 2026-10-10 | ACT-S06-001 | implemented | RETEST-S06-001 | passed | accept_closure

## Retests
Retest ID | Finding ID | Action ID | Evidence IDs | Result | Decision | Executed at
RETEST-S01-001 | FIND-S01-001 | ACT-S01-001 | EVID-S01-RETEST | passed | accept_closure | 2026-09-25T15:10:00Z
RETEST-S03-001 | FIND-S03-001 | ACT-S03-001 | EVID-S03-RETEST | passed | accept_closure | 2026-09-26T02:08:20Z
RETEST-S05-001 | FIND-S05-001 | ACT-S05-001 | EVID-S05-RETEST | passed | accept_closure | 2026-09-26T02:08:20Z
RETEST-S06-001 | FIND-S06-001 | ACT-S06-001 | EVID-S06-RETEST | passed | accept_closure | 2026-09-26T02:08:20Z

## NIST Mapping
Control ID | NIST category
CHG-01 | PR.AA
CHG-01 | PR.PS
CHG-02 | PR.PS
CHG-03 | PR.IR
CHG-03 | PR.PS
CHG-04 | PR.PS
DR-01 | PR.IR
DR-01 | RC.RP
DR-02 | ID.IM
DR-02 | RC.RP
GOV-01 | GV.OC
GOV-01 | GV.RR
GOV-01 | ID.AM
GOV-02 | GV.RM
GOV-02 | ID.RA
GOV-03 | GV.SC
IAM-01 | PR.AA
IAM-02 | PR.AA
IAM-03 | PR.AA
IAM-04 | PR.AA
IAM-05 | PR.AA
IR-01 | DE.AE
IR-01 | DE.CM
IR-02 | RS.AN
IR-02 | RS.MA
OPS-01 | PR.DS
OPS-02 | PR.DS
OPS-02 | RC.RP
OPS-03 | DE.CM
OPS-03 | PR.PS
OPS-04 | ID.RA
OPS-04 | PR.PS

## RMiT Mapping
Control ID | RMiT reference
CHG-01 | RMIT-10.11
CHG-02 | RMIT-10.8
CHG-03 | RMIT-10.11
GOV-03 | RMIT-10.47
IAM-01 | RMIT-10.53
IAM-02 | RMIT-10.53
IAM-02 | RMIT-10.54
IAM-03 | RMIT-10.56
IAM-04 | RMIT-10.55
IAM-05 | RMIT-10.56
IR-01 | RMIT-10.57
OPS-01 | RMIT-10.44
OPS-02 | RMIT-10.44
OPS-03 | RMIT-10.57

## Reconciliation
Measure | Value
record_count.actions | 4
record_count.controls | 20
record_count.evidence | 19
record_count.findings | 4
record_count.retests | 4
record_count.workpapers | 20
control_coverage.assessed | 4
control_coverage.state | partial
control_coverage.total | 20
control_coverage.unassessed | 16
control_coverage.workpapers_missing | 0
control_coverage.workpapers_present | 20
snapshot_id | SNAP-20260926T024908-88653414
unmatched_references | 0

## Limitations
Number | Limitation
1 | This is synthetic, local-lab material and is not evidence from a real institution.
2 | The assessment is self-reviewed and is not an independent audit, certification, or assurance opinion.
3 | 20 of 20 registered controls have frozen workpapers; 4 have executed assessment conclusions in this snapshot.
4 | Evidence payloads, filesystem paths, queries, secrets, and backup contents are intentionally excluded.
5 | PDF artifacts, when present, are local derivatives with a separate render manifest and require visual review before distribution.
6 | All results are frozen to snapshot SNAP-20260926T024908-88653414 at 2026-09-26T02:49:08.830858Z.